## Sheet1
NRM Partnerships Budget and Project Plan 2022-23
6. PROJECT PLAN AND BUDGET EXCERPT
Please detail each of the major works or activities separately in the budget below. Only list activities which achieve the aims of the project (as described in Section 3). Please set these out as one activity per line. All amounts must exclude GST. (An excel sheet budget can also be supplied, and submitted separately) Note: For the in-kind contributions community volunteers can cost an in-kind labour component at $40/hour.
Proposed Activity | Completion by date | Unit of measure | Quantity (C) | Unit cost (exc. GST) (D) | Total activity cost (CxD) | LLS Funds Sought | Applicant contribution (cash and in-kind)
Example | [5 empty] | (excl. GST)
| Enter below | Enter below | Enter below | Enter below | This Column Autocalculates | Enter Below | This Column Autocalculates
Bush regeneration contractors - Initial weed control | 2023-05-01 | hectares | 10 | 1200 | 12000 | 9500 | 2500
Bush regeneration contractors - Follow up weed control | 2023-12-01 | hectares | 10 | 1000 | 10000 | 10000 | 0
Koala Surveys- Spring (audio moth, cameras, landcare surveys) | 2023-10-01 | number | 1 | 15000 | 15000 | 7500 | 7500
Revegetation (500 seedlings, tree guards) | 2023-10-01 | hectares | 3 | 3500 | 10500 | 5000 | 5500
Landcare fauna surveys in kind | 2023-10-01 | hours | 50 | 40 | 2000 | 0 | 2000
NPWS Staff project management | 2024-02-01 | hours | 60 | 50 | 3000 | 0 | 3000
Photo Monitoring | 1/03/2023 and Jan 24 | hours | 28 | 50 | 1400 | 0 | 1400
Maintenance- 12 months weed control (landcare) | 2025-02-01 | hours | 170 | 40 | 6800 | 0 | 6800
Maintenance- Watering, replacement plants 3 months | 2025-02-01 | hours | 42 | 40 | 1680 | 0 | 1680
Additional Fauna Surveys (staff/landcare) | 2025-02-01 | hours | 40 | 40 | 1600 | 0 | 1600
Reporting | May 23 and Feb 24 | each | 2 | 120 | 240 | 0 | 240
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
PROJECT TOTAL (ALL APPLICATIONS |  |  |  |  | 64220 | 32000 | 32220 | 50.17% | < In kind proportion of project
LALC 20% ADMIN FEE (LALCS ONLY)- DELETE IF NOT A LALC | [5 empty] | 6400 | 0
|  |  |  | TOTALS | 64220 | 38400 | 32220
Proposed Activity | Completion by date | Unit of measure | Quantity (C) | Unit cost (exc. GST) (D) | Total activity cost (CxD) | LLS Funds Sought | Applicant contribution (cash and in-kind)- note this section will automatically balance the total.
(excl. GST)
| Enter below | Enter below | Enter below | Enter below | This Column Autocalculates | Enter Below | This Column Autocalculates
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
Photo Monitoring |  |  |  |  | 0 |  | 0
Maintenance |  |  |  |  | 0 |  | 0
Reporting
NEW ROW: Mouse click on line number at left, then Right Click>Insert |  |  |  |  | 0 |  | 0
[5 empty] | 0 |  | 0
PROJECT TOTAL A (ALL APPLICATIONS) |  |  |  |  | 0 | 0 | 0 | #DIV/0! | < In kind proportion of project
PROJECT TOTAL B (A X1.2) LALC 20% ADMIN FEE (LALCS ONLY)- DELETE IF NOT A LALC | [5 empty] | 0 | 0 | If TOTAL A IS ORANGE: CHECK YOUR BUDGET- over maximum budget allowable
|  |  |  | TOTALS | 0 | 0